## Overall Summary Snapshot
Reporting Date | 2025-02-27 | <- populate this date in the same format
The below table is auto populated; do not alter any cell formula
KT STATUS DASHBOARD |  |  | As on | 2025-02-27
| Tower Owner | Overall KT Topics | KT Topics |  | Playback |  | KT Progress (Planned vs. Actual) | Overall KT Progress
|  |  | Planned | Actual | Planned | Actual
All Towers |  | 2312 | 650.5 | 595.25 | 3 | 2 | 91.51% | 25.75%
Corp Apps | John | 671 | 176 | 88 | 0 | 0 | 50% | 13.11% | KT Cancelled due to Holiday(LTIM and TCS)
SAP | Maddy | 947 | 259 | 283 | 0 | 0 | 109.3% | 29.88% | Green
Integration | Richard | 154 | 55 | 51 | 2 | 2 | 92.73% | 33.12%
EIT | Madhav | 75 | 51 | 39 | 0 | 0 | 76.47% | 52%
EDA | Cummins | 392 | 79 | 107 | 0 | 0 | 135.4% | 27.3%
Sharepoint | Sachin | 34 | 14.5 | 12.25 | 0 | 0 | 84.48% | 36.03%
Service Now | Vinod | 28 | 9 | 8 | 0 | 0 | 88.89% | 28.57%
LAN | Prachi | 11 | 7 | 7 | 1 | 0 | 100% | 63.64%
KT STATUS DASHBOARD |  |  | As on | 2025-12-05 |  |  |  |  | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
| Tower Owner | Overall KT Topics | KT Topics |  | Playback |  | KT Progress (Planned vs. Actual) | Overall KT Progress | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07
|  |  | Planned | Actual | Planned | Actual |  |  | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments | Additional Comments
All Towers |  | 2945 | 2945 | 2945 | 98 | 98 | 100% | 100% | bar: 2025-02-28; 2025-03-03 to 2025-03-14; 2025-03-17 to 2025-03-28
Corp Apps | John | 660 | 660 | 660 | 36 | 34 | 100% | 100% | KT Cancelled due to Holiday( LTIM and TCS) |  | Backlog sessions need to be covered. |  |  | Backlog sessions need to be covered. | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green |  |  | All green | All green | KT completed | KT completed | KT completed
SAP | Maddy | 1296 | 1296 | 1295 | 18 | 18 | 99.92% | 99.92% | Green |  | All green |  |  | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green |  |  | All green | All green | All green | KT completed | KT completed
Integration | Richard | 131 | 131 | 131 | 6 | 6 | 100% | 100% | KCD pending fromLTIM on SFG & SSP |  | All green |  |  | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green |  |  | All green | All green | All green | KT completed | KT completed
EIT | Madhav | 348 | 348 | 348 | 12 | 13 | 100% | 100% |  |  | All green |  |  | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green |  |  | All green | All green | KT completed | KT completed | KT completed
EDA | Cummins | 348 | 348 | 348 | 8 | 8 | 100% | 100% |  |  | All green |  |  | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green |  |  | All green | All green | All green | KT completed | KT completed
Sharepoint | Sachin | 35 | 35 | 35 | 11 | 13 | 100% | 100% |  |  | All green |  |  | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green |  |  | All green | All green | KT completed | KT completed | KT completed
Service Now | Vinod | 28 | 28 | 28 | 2 | 2 | 100% | 100% |  |  | All green |  |  | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green |  |  | All green | All green | KT completed | KT completed | KT completed
LAN | Prachi | 11 | 11 | 12 | 5 | 4 | 109.1% | 109.1% |  |  | No session planned for today |  |  | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green |  |  | All green | All green | KT completed | KT completed | KT completed
AS400 | jonny | 88 | 88 | 88 | 2 | 2 | 100% | 100% |  |  | Session cancelled due to unavailability of LTIM SME |  |  | Session cancelled due to unavailability of LTIM SME | LTIM SME is not available for KT last week . Backlog to be covered this week. | LTIM SME is not available for KT last week . Backlog to be covered this week. | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green | All green |  |  | All green | All green | KT completed | KT completed | KT completed
| Tower Owner | Overall KT Topics | KT Topics |  | Playback |  | KT Progress (Planned vs. Actual) | Overall KT Progress | 2025-02-26: 2025-02-26
|  |  | Planned | Actual | Planned | Actual |  |  | 2025-02-26: Additional Comments
All Towers |  | 2340 | 539.25 | 512.25 | 3 | 2 | 94.99% | 21.89%

## Detailed (hidden)
PHINIA KT DASHBOARD
|  |  | Column Auto Populate | M | T | W | T | T | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
Towers | KT Owner | KT Topics | Summary | time axis 2025-02-17 to 2025-04-30
F
All Towers |  | Overall | 25.75% | 98.95% | 106.7% | 210.2% | 188% | 95.28% | 100% | 100% | 97.52% | 84.91% | 62.1% | 74.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Planned | 2312 | 47.5 | 22.5 | 29.5 | 18.75 | 31.75 | 4 | 4 | 110.75 | 119.25 | 131.25 | 131.25 | 81.75 | 12 | 0 | 160.5 | 131.61 | 87.33 | 79.83 | 75.75 | 0 | 0 | 74.75 | 80.75 | 74.25 | 84.14 | 59.14 | 0 | 0 | 49.14 | 59.14 | 67.14 | 56.14 | 94.14 | 0 | 0 | 60 | 46.25 | 49.25 | 71.25 | 49.25 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual | 595.25 | 47 | 24 | 62 | 35.25 | 30.25 | 4 | 4 | 108 | 101.25 | 81.5 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Playback (P) | 35 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Playback (A) | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes
TOWER LEVEL DASHBOARD
Corp Apps | Vijit | Overall
KT Plnd Till Yday | 671 | Planned | 671 | 2025-02-17: 13; 2025-02-18: 0; 2025-02-19: 12; 2025-02-20: 6; 2025-02-21: 13; 2025-02-24: 33; 2025-02-25: 33; 2025-02-26: 33; 2025-02-27: 33; 2025-02-28: 33; 2025-03-03: 44; 2025-03-04: 44; 2025-03-05: 44; 2025-03-06: 44; 2025-03-07: 44; 2025-03-10: 33; 2025-03-11: 33; 2025-03-12: 22; 2025-03-13: 22; 2025-03-14: 22; 2025-03-17: 11; 2025-03-18: 11; 2025-03-19: 11; 2025-03-20: 11; 2025-03-21: 11; 2025-03-24: 11; 2025-03-25: 11; 2025-03-26: 11; 2025-03-27: 11; 2025-03-28: 11
KT Act till Yday | 88 | Actual | 88 | 2025-02-17: 13; 2025-02-18: 0; 2025-02-19: 12; 2025-02-20: 6; 2025-02-21: 13; 2025-02-24: 27; 2025-02-25: 17; 2025-02-26: 0
PlayBack Plnd | 0 | Playback (P) | 0
PlayBack Act | 0 | Playback (A) | 0
|  | Notes |  | 2025-02-24: Balance KT topic will be covered in the next session as planned.; 2025-02-25: Balance KT topic will be covered in the next session. One of resource is OOO from TCS till 27 due to which KT topic will be covered in next session; 2025-02-26: Due to Holiday,associates are not available
SAP | Sachin | Overall
KT Plnd Till Yday | 947 | Planned | 947 | 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 57; 2025-02-25: 57; 2025-02-26: 73; 2025-02-27: 72; 2025-02-28: 21; 2025-03-03: 69; 2025-03-04: 68; 2025-03-05: 21; 2025-03-06: 17; 2025-03-07: 11; 2025-03-10: 16; 2025-03-11: 31; 2025-03-12: 34; 2025-03-13: 45; 2025-03-14: 17; 2025-03-17: 23; 2025-03-18: 32; 2025-03-19: 22; 2025-03-20: 17; 2025-03-21: 56; 2025-03-24: 28; 2025-03-25: 27; 2025-03-26: 31; 2025-03-27: 57; 2025-03-28: 31; 2025-03-31: 14
KT Act till Yday | 283 | Actual | 283 | 2025-02-24: 57; 2025-02-25: 64; 2025-02-26: 64; 2025-02-27: 98
PlayBack Plnd | 5 | Playback (P) | 5 | 2025-02-21: 0; 2025-02-28: 1; 2025-03-03: 1; 2025-03-10: 1; 2025-03-17: 1; 2025-03-24: 1
PlayBack Act | 0 | Playback (A) | 0 | 2025-02-21: 0; 2025-02-28: 0
|  | Notes |  | 2025-02-25: 3 additional OTC topics and 4 addtional MFG topics are covered today; 2025-02-26: MFG and Security sessions are not happening today due to holiday - 17 topics, 64 topics covered today which includes 11 additional topics of OTC; 2025-02-27: 3 Security topics left 2 OTC additional topics 13 PTP topics left will be covered under WM topic 33 MFG additional topcis covered of 3rd and 4th March; 2025-02-28: MFG playback is planned; 2025-03-03: Security playback is planned
Integration | Harshad | Overall
KT Plnd Till Yday | 154 | Planned | 154 | 2025-02-17: 6; 2025-02-18: 6; 2025-02-19: 7; 2025-02-20: 6; 2025-02-21: 6; 2025-02-24: 8; 2025-02-25: 8; 2025-02-26: 4; 2025-02-27: 4; 2025-02-28: 4; 2025-03-03: 6; 2025-03-04: 5; 2025-03-05: 7; 2025-03-06: 9; 2025-03-07: 7; 2025-03-10: 4; 2025-03-11: 2; 2025-03-12: 3; 2025-03-13: 2; 2025-03-14: 1; 2025-03-17: 3; 2025-03-18: 3; 2025-03-19: 2; 2025-03-20: 2; 2025-03-21: 3; 2025-03-24: 3; 2025-03-25: 3; 2025-03-26: 5; 2025-03-27: 3; 2025-03-28: 6; 2025-03-31: 16
KT Act till Yday | 51 | Actual | 51 | 2025-02-17: 6; 2025-02-18: 6; 2025-02-19: 7; 2025-02-20: 6; 2025-02-21: 6; 2025-02-24: 8; 2025-02-25: 8; 2025-02-26: 4
PlayBack Plnd | 5 | Playback (P) | 5 | bar: 2025-02-20; 2025-02-25; 2025-03-04; 2025-03-07; 2025-03-28
PlayBack Act | 2 | Playback (A) | 2 | bar: 2025-02-20; 2025-02-25
|  | Notes |  | 2025-02-20: LTIM yet to prepare KCD docs. Hence only 6 covered out of 11; 2025-02-21: 2 topics (KCD signoff of SFG) of 20th Feb is yet to be completed. Responsible LTIM.; 2025-02-24: 2 topics (KCD signoff of SFG) of 20th Feb is yet to be completed. Responsible LTIM.; 2025-02-25: 2 topics (KCD signoff of SFG) of 20th Feb is yet to be completed. 5 topics (KCD & signoff of SSP) of 25th Feb is yet to be Responsible LTIM.; 2025-02-26: KCD Signoff pending from LTIM on SFG.KCD doc yet to receive for SSP from LTIM.
EIT | Chendra | Overall
KT Plnd Till Yday | 75 | Planned | 75 | 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 3; 2025-02-21: 4; 2025-02-22: 4; 2025-02-23: 4; 2025-02-24: 4; 2025-02-25: 9; 2025-02-26: 11; 2025-02-27: 12; 2025-02-28: 12; 2025-03-01: 12
KT Act till Yday | 39 | Actual | 39 | 2025-02-20: 3; 2025-02-21: 4; 2025-02-22: 4; 2025-02-23: 4; 2025-02-24: 4; 2025-02-25: 9; 2025-02-26: 11
PlayBack Plnd | 0 | Playback (P) | 0 | 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0
PlayBack Act | 0 | Playback (A) | 0 | 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0
Notes
EDA | Ajay | Overall
KT Plnd Till Yday | 392 | Planned | 392 | 2025-02-17: 21; 2025-02-18: 15; 2025-02-19: 7; 2025-02-20: 0; 2025-02-21: 7; 2025-02-24: 6; 2025-02-25: 8; 2025-02-26: 8; 2025-02-27: 7; 2025-02-28: 10; 2025-03-03: 39; 2025-03-04: 12; 2025-03-05: 10; 2025-03-06: 8; 2025-03-07: 13; 2025-03-10: 20; 2025-03-11: 13; 2025-03-12: 12; 2025-03-13: 11; 2025-03-14: 8; 2025-03-17: 11; 2025-03-18: 13; 2025-03-19: 32; 2025-03-20: 25; 2025-03-21: 24; 2025-03-24: 17; 2025-03-25: 5; 2025-03-26: 2; 2025-03-31: 28
KT Act till Yday | 107 | Actual | 107 | 2025-02-17: 21; 2025-02-18: 15; 2025-02-19: 39; 2025-02-20: 16; 2025-02-21: 4; 2025-02-24: 10; 2025-02-25: 2
PlayBack Plnd | 8 | Playback (P) | 8 | 2025-03-24: 6; 2025-03-25: 1; 2025-03-26: 1
PlayBack Act | 0 | Playback (A) | 0 | 2025-02-21: 0
|  | Notes |  | 2025-02-20: Document review & History tickets covered before schedule; 2025-02-21: Few points covered yesterday. Play back moced to thrusday as per LTIM request; 2025-02-25: Few points covered yesterday.
Sharepoint | Sandeep | Overall
KT Plnd Till Yday | 34 | Planned | 34 | 2025-02-17: 0.5; 2025-02-18: 0.5; 2025-02-19: 1.5; 2025-02-20: 2.5; 2025-02-21: 1.5; 2025-02-24: 1.5; 2025-02-25: 3; 2025-02-26: 1.25; 2025-02-27: 2.25; 2025-02-28: 1.25; 2025-03-03: 1.25; 2025-03-04: 1.36; 2025-03-05: 3.33; 2025-03-06: 0.33; 2025-03-07: 0.25; 2025-03-10: 1.25; 2025-03-11: 1.25; 2025-03-12: 1.25; 2025-03-13: 1.14; 2025-03-14: 1.14; 2025-03-17: 1.14; 2025-03-18: 0.14; 2025-03-19: 0.14; 2025-03-20: 1.14; 2025-03-21: 0.14; 2025-03-24: 1; 2025-03-25: 0.25; 2025-03-26: 0.25; 2025-03-27: 0.25; 2025-03-28: 1.25
KT Act till Yday | 12.25 | Actual | 12.25 | 2025-02-17: 1; 2025-02-18: 1; 2025-02-19: 2; 2025-02-20: 3; 2025-02-21: 2; 2025-02-24: 2; 2025-02-25: 0; 2025-02-26: 1.25
PlayBack Plnd | 11 | Playback (P) | 11 | 2025-02-21: 0; 2025-02-28: 0; 2025-03-06: 1; 2025-03-07: 1; 2025-03-14: 0; 2025-03-21: 0; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-31: 2; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1
PlayBack Act | 0 | Playback (A) | 0 | 2025-02-21: 0; 2025-02-28: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-14: 0; 2025-03-21: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0
|  | Notes |  | 2025-02-25: Sessions are cnacelled , But sessions are covered earlier
Service Now | Dilip | Overall
KT Plnd Till Yday | 28 | Planned | 28 | 2025-02-17: 6; 2025-02-18: 0; 2025-02-19: 1; 2025-02-20: 0.25; 2025-02-21: 0.25; 2025-02-24: 0.25; 2025-02-25: 0.25; 2025-02-26: 0; 2025-02-27: 1; 2025-02-28: 0.5; 2025-03-03: 0.25; 2025-03-04: 0.25; 2025-03-05: 1; 2025-03-06: 0.5; 2025-03-07: 0.5; 2025-03-10: 0.5; 2025-03-11: 0.5; 2025-03-12: 2; 2025-03-13: 3; 2025-03-14: 10
KT Act till Yday | 8 | Actual | 8 | 2025-02-17: 5; 2025-02-18: 1; 2025-02-19: 1; 2025-02-20: 0.25; 2025-02-21: 0.25; 2025-02-24: 0; 2025-02-25: 0.25; 2025-02-26: 0.25
PlayBack Plnd | 1 | Playback (P) | 1 | 2025-02-21: 0; 2025-03-14: 1
PlayBack Act | 0 | Playback (A) | 0 | 2025-02-21: 0; 2025-03-14: 0
|  | Notes |  | 2025-02-20: CMDB is scheduled for 4 days
LAN | Neel | Overall |  | 2025-02-24: Session cancelled -Sick leave
KT Plnd Till Yday | 11 | Planned | 11 | 2025-02-17: 1; 2025-02-18: 1; 2025-02-19: 1; 2025-02-20: 1; 2025-02-21: 0; 2025-02-24: 1; 2025-02-25: 1; 2025-02-26: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1
KT Act till Yday | 7 | Actual | 7 | 2025-02-17: 1; 2025-02-18: 1; 2025-02-19: 1; 2025-02-20: 1; 2025-02-21: 1; 2025-02-24: 0; 2025-02-25: 1; 2025-02-26: 1
PlayBack Plnd | 5 | Playback (P) | 5 | bar: 2025-02-21; 2025-02-28; 2025-03-07; 2025-03-13 to 2025-03-14
PlayBack Act | 0 | Playback (A) | 0 | 2025-02-21: 0
Notes
AS400 Apps | Naga | Overall
KT Plnd Till Yday | 42 | Planned | 42 | 2025-02-17: 4; 2025-02-18: 4; 2025-02-19: 2; 2025-02-20: 1; 2025-02-21: 2; 2025-02-24: 2; 2025-02-25: 2; 2025-02-26: 3; 2025-02-27: 1; 2025-02-28: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 1; 2025-03-14: 1; 2025-03-17: 1; 2025-03-18: 1; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1
KT Act till Yday | 15 | Actual | 15 | 2025-02-17: 4; 2025-02-18: 4; 2025-02-19: 2; 2025-02-20: 1; 2025-02-21: 2; 2025-02-24: 2; 2025-02-25: 0; 2025-02-26: 0
PlayBack Plnd | 0 | Playback (P) | 0
PlayBack Act | 0 | Playback (A) | 0
|  | Notes |  | 2025-02-25: LTIM Associate OOO till 3rd March; 2025-02-26: LTIM Associate OOO till 3rd March
Note on D6: Do not Edit the cells in this column - Auto populated values

## Detailed New-backup (hidden)
|  | All Tower Combined Status |  |  |  |  | Corp Apps: Vijith |  |  |  |  | SAP: Sachin |  |  |  |  | Integration: Harshad |  |  |  |  | EIT: Chendra |  |  |  |  | EDA: Ajay |  |  |  |  | SharePoint: Sandeep |  |  |  |  | SNOW: Dilip |  |  |  |  | LAN: Neel |  |  |  |  | AS400: Naga |  |  |  |  | SIAM :
[7 empty] | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today %
[7 empty] | 671 | 385 | 2 | 2 | 57.38% | 1323 | 643 | 9 | 2 | 48.6% | 154 | 86 | 5 | 3 | 55.84% | 94 | 93 | 1 | 1 | 98.94% | 392 | 180 | 8 | 3 | 45.92% | 34 | 24.27 | 11 | 1 | 71.38% | 28 | 11.5 | 1 | 0 | 41.07% | 11 | 11 | 5 | 1 | 100% | 78 | 27 | 2 | 0 | 34.62% | 15 | 10 | 2 | 2 | 66.67%
| KT Topics | Overall | Planned | Actual | Playback (P) | Playback (A) | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes
| Overall Summary | 52.45% | 2785 | 1460.77 | 44 | 13 | 671 | 385 | 2 | 2 |  | 1323 | 643 | 9 | 2 |  | 154 | 86 | 5 | 3 |  | 94 | 93 | 1 | 1 |  | 392 | 180 | 8 | 3 |  | 34 | 24.27 | 11 | 1 |  | 28 | 11.5 | 1 | 0 |  | 11 | 11 | 5 | 1 |  | 78 | 27 | 2 | 0 |  | 15 | 10 | 2 | 2
M | 2025-02-17 | 99.03% | 51.5 | 51 | 0 | 0 | 13 | 13 |  |  |  | 0 |  |  |  |  | 6 | 6 |  |  |  | 0 |  |  |  |  | 21 | 21 |  |  |  | 0.5 | 1 |  |  |  | 6 | 5 |  |  |  | 1 | 1 |  |  |  | 4 | 4
T | 2025-02-18 | 105.7% | 26.5 | 28 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  |  | 6 | 6 |  |  |  | 0 |  |  |  |  | 15 | 15 |  |  |  | 0.5 | 1 |  |  |  | 0 | 1 |  |  |  | 1 | 1 |  |  |  | 4 | 4
W | 2025-02-19 | 203.2% | 31.5 | 64 | 0 | 0 | 12 | 12 |  |  |  | 0 |  |  |  |  | 7 | 7 |  |  |  | 0 |  |  |  |  | 7 | 39 |  |  |  | 1.5 | 2 |  |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  |  | 2 | 2 |  |  |  | 2 | 2 |  |  | Incident & Complaints Mgmt Completed
T | 2025-02-20 | 175.9% | 21.75 | 38.25 | 1 | 1 | 6 | 6 |  |  |  | 0 |  |  |  |  | 6 | 6 | 1 | 1 | LTIM yet to prepare KCD docs. | 4 | 4 |  |  |  | 0 | 16 |  |  | Document review & History tickets covered before schedule | 2.5 | 3 |  |  |  | 0.25 | 0.25 |  |  | CMDB is scheduled for 4 days | 1 | 1 |  |  |  | 2 | 2
F | 2025-02-21 | 96.13% | 38.75 | 37.25 | 1 | 0 | 13 | 13 |  |  |  | 0 |  | 0 | 0 |  | 6 | 6 |  |  |  | 8 | 8 |  |  |  | 7 | 4 |  |  | Few points covered yesterday. Play back moced to thrusday as per LTIM request | 1.5 | 2 |  |  |  | 0.25 | 0.25 |  |  |  | 0 | 1 | 1 | 0 |  | 3 | 3
Week Status |  | 128.5% | 170 | 218.5 | 2 | 1 | 44 | 44 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 31 | 31 | 1 | 1 |  | 12 | 12 | 0 | 0 |  | 50 | 95 | 0 | 0 |  | 6.5 | 9 | 0 | 0 |  | 7.5 | 7.5 | 0 | 0 |  | 4 | 5 | 1 | 0 |  | 15 | 15 | 0 | 0
M | 2025-02-24 | 97.68% | 118.75 | 116 | 0 | 0 | 33 | 27 |  |  | Balance KT topic will be covered in the next session as planned. | 57 | 57 |  |  |  | 8 | 8 |  |  |  | 10 | 10 |  |  |  | 6 | 10 |  |  |  | 1.5 | 2 |  |  |  | 0.25 | 0 |  |  |  | 1 | 0 |  |  | Covered KT on 21st Feb and Playback Session was not happened on 21st Feb. | 2 | 2 |  |  |  | 1 | 1
T | 2025-02-25 | 84.65% | 117.25 | 99.25 | 1 | 1 | 33 | 17 |  |  | Balance KT topic will be covered in the next session. One of resource is OOO from TCS till 27 due to which KT topic will be covered in next session | 57 | 64 |  |  |  | 8 | 8 | 1 | 1 |  | 7 | 7 |  |  |  | 8 | 2 |  |  | Few points covered yesterday. | 3 | 0 |  |  | Sessions are cnacelled , But sessions are covered earlier | 0.25 | 0.25 |  |  |  | 1 | 1 |  |  |  | 0 | 0 |  |  | LTIM Associate OOO till 3rd March | 1 | 1
W | 2025-02-26 | 62.1% | 131.25 | 81.5 | 0 | 0 | 33 | 0 |  |  | Due to Holiday,both LTIM & TCS associates are not available | 73 | 64 |  |  |  | 4 | 4 |  |  |  | 11 | 11 |  |  |  | 8 |  |  |  | Few points covered yesterday. | 1.25 | 1.25 |  |  |  | 0 | 0.25 |  |  |  | 1 | 1 |  |  |  | 0 | 0 |  |  | LTIM Associate OOO till 3rd March | 2 | 2
T | 2025-02-27 | 111% | 127.25 | 141.25 | 0 | 2 | 33 | 22 |  |  |  | 72 | 98 |  |  |  | 4 | 4 |  |  |  | 8 | 8 |  |  |  | 7 | 7 |  | 2 |  | 2.25 | 1.25 |  |  |  | 1 | 1 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | LTIM Associate OOO till 3rd March
F | 2025-02-28 | 138.1% | 99.75 | 137.75 | 2 | 3 | 33 | 64 |  |  |  | 37 | 47 | 1 | 1 |  | 4 | 4 |  |  |  | 14 | 14 |  |  |  | 10 | 6 |  | 1 |  | 1.25 | 2.25 |  |  |  | 0.5 | 0.5 |  |  |  | 0 | 0 | 1 | 1 |  | 0 | 0 |  |  | LTIM Associate OOO till 3rd March | 1 | 1 |  |  | Knowledge Mgmt Completed
Week Status |  | 96.89% | 594.25 | 575.75 | 3 | 6 | 165 | 130 | 0 | 0 |  | 296 | 330 | 1 | 1 | 111.5% | 28 | 28 | 1 | 1 |  | 50 | 50 | 0 | 0 |  | 39 | 25 | 0 | 3 |  | 9.25 | 6.75 | 0 | 0 |  | 2 | 2 | 0 | 0 |  | 3 | 2 | 1 | 1 |  | 2 | 2 | 0 | 0 |  | 5 | 5 | 0 | 0
M | 2025-03-03 | 102.1% | 245.5 | 250.75 | 1 | 2 | 44 | 68 |  |  |  | 142 | 123 | 1 | 1 |  | 6 | 6 |  |  | KCD Signoff pending from LTIM on SFG KCD doc yet to receive for SSP from LTIM ETA: 04-Mar | 12 | 12 |  |  |  | 39 | 39 |  |  |  | 1.25 | 1.5 | 0 | 1 | Sessions cancelled on 25th Feb is covered today . | 0.25 | 0.25 |  |  |  | 1 | 1 |  |  |  | 0 | 0 |  |  | LTIM Associate on Sick leave |  |  | 1 | 1
T | 2025-03-04 | 101.3% | 153.61 | 155.61 | 2 | 2 | 44 | 55 | 1 | 1 | All the back logs completed | 79 | 74 |  |  |  | 5 | 5 | 1 | 1 | KCD Signoff pending from LTIM on SFG KCD doc yet to receive for SSP from LTIM ETA: 04-Mar | 8 | 8 |  |  |  | 12 | 8 |  |  | few topics covered in initial week | 1.36 | 1.36 |  |  |  | 0.25 | 0.25 |  |  |  | 1 | 1 |  |  |  | 3 | 3 |  |  |  | 2 | 2 | 1 | 1 | Problem Mgmt Completed. Incident & KM Playback Session Done
W | 2025-03-05 | 100.7% | 150.33 | 151.33 | 0 | 0 | 44 | 44 |  |  |  | 73 | 74 |  |  |  | 7 | 7 |  |  | KCD Signoff pending from LTIM on SFG KCD doc yet to receive for SSP from LTIM ETA: 04-Mar | 7 | 7 |  |  |  | 10 | 9 |  |  |  | 3.33 | 4.33 |  |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  |  | 4 | 4 |  |  |  | 1 | 1
T | 2025-03-06 | 129.8% | 83.83 | 108.83 | 3 | 2 | 44 | 44 | 1 | 1 |  | 14 | 42 |  |  |  | 9 | 9 |  |  | KCD Signoff pending from LTIM on SFG KCD doc yet to receive for SSP from LTIM ETA: 04-Mar | 4 | 4 | 1 | 1 |  | 8 | 4 |  |  | Topics duration was more | 0.33 | 1.33 | 1 | 0 | Playback moved postponed to next week | 0.5 | 0.5 |  |  |  | 1 | 1 |  |  |  | 3 | 3 |  |  |  | 5
F | 2025-03-07 | 0% | 79.75 | 0 | 6 | 0 | 44 |  |  |  |  | 12 |  | 2 |  |  | 7 |  | 1 |  |  | 1 |  |  |  |  | 13 |  |  |  |  | 0.25 |  | 1 |  |  | 0.5 | [6 empty] | 1 |  |  | 2 |  | 1
Week Status |  | 93.48% | 713.02 | 666.52 | 12 | 6 | 220 | 211 | 2 | 2 |  | 320 | 313 | 3 | 1 | 97.81% | 34 | 27 | 2 | 1 |  | 32 | 31 | 1 | 1 |  | 82 | 60 | 0 | 0 |  | 6.52 | 8.52 | 2 | 1 |  | 2.5 | 2 | 0 | 0 |  | 4 | 4 | 1 | 0 |  | 12 | 10 | 1 | 0 |  | 8 | 3 | 2 | 2
M | 2025-03-10 | 0% | 111.75 | 0 | 1 | 0 | 33 |  |  |  |  | 51 |  | 1 |  |  | 4 | [9 empty] | 20 |  |  |  |  | 1.25 |  |  |  |  | 0.5 | [9 empty] | 2
T | 2025-03-11 | 0% | 97.75 | 0 | 0 | 0 | 33 |  |  |  |  | 44 |  |  |  |  | 2 | [9 empty] | 13 |  |  |  |  | 1.25 |  |  |  |  | 0.5 | [9 empty] | 4 |  |  |  |  | 0
W | 2025-03-12 | 0% | 96.25 | 0 | 0 | 0 | 22 |  |  |  |  | 52 |  |  |  |  | 3 | [9 empty] | 12 |  |  |  |  | 1.25 |  |  |  |  | 2 | [9 empty] | 4
T | 2025-03-13 | 0% | 113.14 | 0 | 1 | 0 | 22 |  |  |  |  | 70 |  |  |  |  | 2 | [9 empty] | 11 |  |  |  |  | 1.14 |  |  |  |  | 3 | [6 empty] | 1 |  |  | 4
F | 2025-03-14 | 0% | 63.14 | 0 | 3 | 0 | 22 |  |  |  |  | 17 |  | 1 |  |  | 1 | [9 empty] | 8 |  |  |  |  | 1.14 |  |  |  |  | 10 |  | 1 |  |  |  |  | 1 |  |  | 4
Week Status |  | 0% | 482.03 | 0 | 5 | 0 | 132 | 0 | 0 | 0 |  | 234 | 0 | 2 | 0 |  | 12 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 64 | 0 | 0 | 0 |  | 6.03 | 0 | 0 | 0 |  | 16 | 0 | 1 | 0 |  | 0 | 0 | 2 | 0 |  | 18 | 0 | 0 | 0
M | 2025-03-17 | 0% | 91.14 | 0 | 1 | 0 | 11 |  |  |  |  | 61 |  | 1 |  |  | 3 | [9 empty] | 11 |  |  |  |  | 1.14 | [8 empty] | SECONDARY SUPPORT |  |  |  |  | SECONDARY SUPPORT | 4
T | 2025-03-18 | 0% | 138.14 | 0 | 0 | 0 | 11 |  |  |  |  | 107 |  |  |  |  | 3 | [9 empty] | 13 |  |  |  |  | 0.14 | [14 empty] | 4
W | 2025-03-19 | 0% | 91.14 | 0 | 0 | 0 | 11 |  |  |  |  | 44 |  |  |  |  | 2 | [9 empty] | 32 |  |  |  |  | 0.14 | [14 empty] | 2
T | 2025-03-20 | 0% | 60.14 | 0 | 1 | 0 | 11 |  |  |  |  | 17 |  | 1 |  |  | 2 | [9 empty] | 25 |  |  |  |  | 1.14 | [14 empty] | 4
F | 2025-03-21 | 0% | 98.14 | 0 | 1 | 0 | 11 |  |  |  |  | 56 |  |  |  |  | 3 | [9 empty] | 24 |  |  |  |  | 0.14 | [14 empty] | 4 |  | 1
Week Status |  | 0% | 478.7 | 0 | 3 | 0 | 55 | 0 | 0 | 0 |  | 285 | 0 | 2 | 0 |  | 13 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 105 | 0 | 0 | 0 | 14 Topics + 2 Play back were tagged to weekend. Move to weekdays | 2.7 | 0 | 0 | 0 | [11 empty] | 18 | 0 | 1 | 0
M | 2025-03-24 | 0% | 64 | 0 | 7 | 0 | 11 |  |  |  |  | 28 |  | 1 |  |  | 3 | [9 empty] | 17 |  | 6 |  |  | 1 | [14 empty] | 4
T | 2025-03-25 | 0% | 50.25 | 0 | 1 | 0 | 11 |  |  |  |  | 27 |  |  |  |  | 3 | [9 empty] | 5 |  | 1 |  |  | 0.25 | [14 empty] | 4
W | 2025-03-26 | 0% | 51.25 | 0 | 2 | 0 | 11 |  |  |  |  | 31 |  |  |  |  | 5 | [9 empty] | 2 |  | 1 |  |  | 0.25 |  | 1 | [12 empty] | 2
T | 2025-03-27 | 0% | 73.25 | 0 | 1 | 0 | 11 |  |  |  |  | 57 |  |  |  |  | 3 | [14 empty] | 0.25 |  | 1 | [12 empty] | 2
F | 2025-03-28 | 0% | 50.25 | 0 | 2 | 0 | 11 |  |  |  |  | 31 |  |  |  |  | 6 |  | 1 | [12 empty] | 1.25 |  | 1 | [12 empty] | 1
Week Status |  | 0% | 289 | 0 | 13 | 0 | 55 | 0 | 0 | 0 |  | 174 | 0 | 1 | 0 |  | 20 | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  | 24 | 0 | 8 | 0 |  | 3 | 0 | 3 | 0 | [11 empty] | 13 | 0 | 0 | 0
M | 2025-03-31 | 0% | 58 | 0 | 2 | 0 |  |  |  |  | SECONDARY SUPPORT | 14 |  |  |  | SECONDARY SUPPORT | 16 | [8 empty] | SECONDARY SUPPORT | 28 |  |  |  | SECONDARY SUPPORT |  |  | 2
T | 2025-04-01 | 0% | 0 | 0 | 1 | 0 | [27 empty] | 1
W | 2025-04-02 | 0% | 0 | 0 | 1 | 0 | [27 empty] | 1
T | 2025-04-03 | 0% | 0 | 0 | 1 | 0 | [27 empty] | 1
F | 2025-04-04 | 0% | 0 | 0 | 1 | 0 | [27 empty] | 1
Week Status |  | 0% | 58 | 0 | 6 | 0 | [10 empty] | 16 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 6 | 0
M | 2025-04-07 | 0% | 0 | 0 | 0 | 0 | [14 empty] | SECONDARY | [14 empty] | SECONDARY |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY
T | 2025-04-08 | 0% | 0 | 0 | 0 | 0
W | 2025-04-09 | 0% | 0 | 0 | 0 | 0
T | 2025-04-10 | 0% | 0 | 0 | 0 | 0
F | 2025-04-11 | 0% | 0 | 0 | 0 | 0
Week Status |  | 0% | 0 | 0 | 0 | 0
M | 2025-04-14 | 0% | 0 | 0 | 0 | 0
T | 2025-04-15 | 0% | 0 | 0 | 0 | 0
W | 2025-04-16 | 0% | 0 | 0 | 0 | 0
T | 2025-04-17 | 0% | 0 | 0 | 0 | 0
F | 2025-04-18 | 0% | 0 | 0 | 0 | 0
Week Status |  | 0% | 0 | 0 | 0 | 0
M | 2025-04-21 | 0% | 0 | 0 | 0 | 0 |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY
T | 2025-04-22 | 0% | 0 | 0 | 0 | 0
W | 2025-04-23 | 0% | 0 | 0 | 0 | 0
T | 2025-04-24 | 0% | 0 | 0 | 0 | 0
F | 2025-04-25 | 0% | 0 | 0 | 0 | 0
Week Status |  | 0% | 0 | 0 | 0 | 0
M | 2025-04-28 | 0% | 0 | 0 | 0 | 0 | [30 empty] | Handed Off |  |  |  |  | Handed Off
T | 2025-04-29 | 0% | 0 | 0 | 0 | 0
W | 2025-04-30 | 0% | 0 | 0 | 0 | 0
Formulas:
KT Topics = [KT Topics, row above]+1

## Detailed New
TCS Transition Dashboard
All Tower Combined Status | [6 empty] | Corp Apps |  |  |  |  | SAP |  |  |  |  | Integration |  |  |  |  | EIT |  |  |  |  | EDA |  |  |  |  | SharePoint |  |  |  |  | SNOW |  |  |  |  | LAN |  |  |  |  | AS400 |  |  |  |  | SIAM
[7 empty] | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today % | KT (P) Till today | KT (A) Till today | PlayBack (P) | PlayBack (A) | KT till today %
[7 empty] | 660 | 660 | 36 | 34 | 100% | 1296 | 1295 | 18 | 18 | 99.92% | 131 | 131 | 6 | 6 | 100% | 348 | 348 | 12 | 13 | 100% | 348 | 348 | 8 | 8 | 100% | 35 | 35 | 11 | 13 | 100% | 28 | 28 | 2 | 2 | 100% | 11 | 12 | 5 | 4 | 109.1% | 88 | 88 | 2 | 2 | 100% | 19 | 19 | 19 | 19 | 100%
KT Topics |  | Overall | Planned | Actual | Playback (P) | Playback (A) | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes | Planned | Actual | Playback (P) | Playback (A) | Notes
Overall Summary |  | 100% | 2945 | 2945 | 100 | 99 | 660 | 660 | 36 | 34 | 100% | 1296 | 1295 | 18 | 18 | 99.92% | 131 | 131 | 6 | 6 | 100% | 348 | 348 | 12 | 13 | 100% | 348 | 348 | 8 | 8 | 100% | 35 | 35 | 11 | 13 | 100% | 28 | 28 | 2 | 2 | 100% | 11 | 12 | 5 | 4 | 109.1% | 88 | 88 | 2 | 2 | 100% | 19 | 19 | 19 | 19 | 100%
M | 2025-02-17 | 99.03% | 51.5 | 51 | 0 | 0 | 13 | 13 |  |  |  | 0 |  |  |  |  | 6 | 6 |  |  |  | 0 |  |  |  |  | 21 | 21 |  |  |  | 0.5 | 1 |  |  |  | 6 | 5 |  |  |  | 1 | 1 |  |  |  | 4 | 4
T | 2025-02-18 | 105.7% | 26.5 | 28 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  |  | 6 | 6 |  |  |  | 0 |  |  |  |  | 15 | 15 |  |  |  | 0.5 | 1 |  |  |  | 0 | 1 |  |  |  | 1 | 1 |  |  |  | 4 | 4
W | 2025-02-19 | 203.2% | 31.5 | 64 | 0 | 0 | 12 | 12 |  |  |  | 0 |  |  |  |  | 7 | 7 |  |  |  | 0 |  |  |  |  | 7 | 39 |  |  |  | 1.5 | 2 |  |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  |  | 2 | 2 |  |  |  | 1.5 | 1.5
T | 2025-02-20 | 189.7% | 21.75 | 41.25 | 1 | 1 | 6 | 6 |  |  |  | 0 |  |  |  |  | 5 | 5 | 1 | 1 |  | 5 | 8 |  |  |  | 0 | 16 |  |  |  | 2.5 | 3 |  |  |  | 0.25 | 0.25 |  |  |  | 1 | 1 |  |  |  | 2 | 2
F | 2025-02-21 | 96.13% | 38.75 | 37.25 | 1 | 0 | 13 | 13 |  |  |  | 0 |  | 0 | 0 |  | 6 | 6 |  |  |  | 8 | 8 |  |  |  | 7 | 4 |  |  |  | 1.5 | 2 |  |  |  | 0.25 | 0.25 |  |  |  | 0 | 1 | 1 | 0 |  | 3 | 3
Week Status |  | 130.3% | 170 | 221.5 | 2 | 1 | 44 | 44 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 30 | 30 | 1 | 1 |  | 13 | 16 | 0 | 0 |  | 50 | 95 | 0 | 0 |  | 6.5 | 9 | 0 | 0 |  | 7.5 | 7.5 | 0 | 0 |  | 4 | 5 | 1 | 0 |  | 15 | 15 | 0 | 0
M | 2025-02-24 | 97.88% | 129.75 | 127 | 0 | 0 | 33 | 27 |  |  |  | 57 | 57 |  |  |  | 8 | 8 |  |  |  | 21 | 21 |  |  |  | 6 | 10 |  |  |  | 1.5 | 2 |  |  |  | 0.25 | 0 |  |  |  | 1 | 0 |  |  |  | 2 | 2 |  |  |  | 3 | 3
T | 2025-02-25 | 81.94% | 116.25 | 95.25 | 1 | 1 | 33 | 17 |  |  |  | 57 | 64 |  |  |  | 7 | 7 | 1 | 1 |  | 7 | 4 |  |  |  | 8 | 2 |  |  |  | 3 | 0 |  |  |  | 0.25 | 0.25 |  |  |  | 1 | 1 |  |  |  | 0 | 0 |  |  |  | 1 | 1
W | 2025-02-26 | 64.7% | 135.25 | 87.5 | 0 | 0 | 33 | 0 |  |  |  | 73 | 64 |  |  |  | 4 | 4 |  |  |  | 15 | 17 |  |  |  | 8 |  |  |  |  | 1.25 | 1.25 |  |  |  | 0 | 0.25 |  |  |  | 1 | 1 |  |  |  | 0 | 0 |  |  |  | 2.5 | 2.5
T | 2025-02-27 | 107% | 129.25 | 138.25 | 0 | 2 | 33 | 22 |  |  |  | 72 | 98 |  |  |  | 4 | 4 |  |  |  | 10 | 5 |  |  |  | 7 | 7 |  | 2 |  | 2.25 | 1.25 |  |  |  | 1 | 1 |  |  |  | 0 | 0 |  |  |  | 0 | 0
F | 2025-02-28 | 136.7% | 100.75 | 137.75 | 3 | 3 | 33 | 64 |  |  |  | 37 | 47 | 1 | 1 |  | 4 | 4 |  |  |  | 15 | 14 |  |  |  | 10 | 6 |  | 1 |  | 1.25 | 2.25 |  |  |  | 0.5 | 0.5 | 1 | 0 |  | 0 | 0 | 1 | 1 |  | 0 | 0 |  |  |  | 1 | 1
Week Status |  | 95.83% | 611.25 | 585.75 | 4 | 6 | 165 | 130 | 0 | 0 |  | 296 | 330 | 1 | 1 | 111.5% | 27 | 27 | 1 | 1 |  | 68 | 61 | 0 | 0 |  | 39 | 25 | 0 | 3 |  | 9.25 | 6.75 | 0 | 0 |  | 2 | 2 | 1 | 0 |  | 3 | 2 | 1 | 1 |  | 2 | 2 | 0 | 0 |  | 7.5 | 7.5 | 0 | 0
M | 2025-03-03 | 104.3% | 240.5 | 250.75 | 1 | 2 | 44 | 68 |  |  |  | 142 | 123 | 1 | 1 |  | 6 | 6 |  |  |  | 7 | 12 |  |  |  | 39 | 39 |  |  |  | 1.25 | 1.5 | 0 | 1 |  | 0.25 | 0.25 |  |  |  | 1 | 1 |  |  |  | 0 | 0 |  |  |  | 2 | 2 | 2 | 2
T | 2025-03-04 | 96.26% | 160.61 | 154.61 | 2 | 2 | 44 | 55 | 1 | 1 |  | 79 | 74 |  |  |  | 4 | 4 | 1 | 1 |  | 16 | 8 |  |  |  | 12 | 8 |  |  |  | 1.36 | 1.36 |  |  |  | 0.25 | 0.25 |  |  |  | 1 | 1 |  |  |  | 3 | 3 |  |  |  | 2 | 2 | 4.5 | 4.5
W | 2025-03-05 | 96.14% | 155.33 | 149.33 | 3 | 1 | 44 | 44 |  |  |  | 73 | 74 |  |  |  | 7 | 7 |  |  |  | 12 | 5 | 3 | 1 |  | 10 | 9 |  |  |  | 3.33 | 4.33 |  |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  |  | 4 | 4 |  |  |  | 1 | 1
T | 2025-03-06 | 126.4% | 90.84 | 114.84 | 2 | 2 | 44 | 44 | 1 | 1 |  | 14 | 42 |  |  |  | 9 | 9 |  |  |  | 11 | 10 |  | 1 |  | 8 | 4 |  |  |  | 0.34 | 1.34 | 1 | 0 |  | 0.5 | 0.5 |  |  |  | 1 | 1 |  |  |  | 3 | 3 |  |  |  | 5 | 0
F | 2025-03-07 | 105.4% | 71.75 | 75.63 | 9 | 7 | 33 | 33 | 1 | 1 |  | 11 | 13 | 2 | 2 |  | 6 | 6 | 1 | 1 |  | 6 | 13 | 2 | 1 |  | 13 | 8 |  |  |  | 0.25 | 0.13 | 1 | 1 |  | 0.5 | 0.5 | [5 empty] | 1 | 1 |  | 2 | 2 | 1
Week Status |  | 103.6% | 719.03 | 745.16 | 17 | 14 | 209 | 244 | 3 | 3 |  | 319 | 326 | 3 | 3 | 102.2% | 32 | 32 | 2 | 2 |  | 52 | 48 | 5 | 3 |  | 82 | 68 | 0 | 0 |  | 6.53 | 8.66 | 2 | 2 |  | 2.5 | 2.5 | 0 | 0 |  | 4 | 4 | 1 | 1 |  | 12 | 12 | 1 | 0 |  | 10 | 5 | 6.5 | 6.5
M | 2025-03-10 | 87.66% | 210.75 | 184.75 | 3 | 3 | 33 | 33 |  |  |  | 72 | 82 | 1 | 1 |  | 2 | 2 |  |  |  | 80 | 52 | 2 | 1 |  | 20 | 12 |  |  |  | 1.25 | 1.25 | 0 | 1 |  | 0.5 | 0.5 | [8 empty] | 2 | 2
T | 2025-03-11 | 133.1% | 108.75 | 144.75 | 0 | 2 | 33 | 33 |  |  |  | 54 | 62 |  |  |  | 2 | 2 |  |  |  | 1 | 36 |  | 1 |  | 13 | 6 |  |  |  | 1.25 | 1.25 | 0 | 1 |  | 0.5 | 0.5 | [8 empty] | 4 | 4 |  |  |  | 0 | 5
W | 2025-03-12 | 154.5% | 97.25 | 150.25 | 0 | 2 | 22 | 22 |  |  |  | 33 | 73 |  |  |  | 3 | 3 |  |  |  | 20 | 33 |  |  |  | 12 | 10 |  | 1 |  | 1.25 | 2.25 |  |  |  | 2 | 2 | 0 | 1 |  | 0 | 1 |  |  |  | 4 | 4
T | 2025-03-13 | 100% | 116.14 | 116.14 | 3 | 3 | 22 | 22 | 1 | 1 |  | 53 | 27 | 1 | 1 |  | 2 | 2 |  |  |  | 20 | 44 |  | 1 |  | 11 | 13 |  |  |  | 1.14 | 1.14 |  |  |  | 3 | 3 | [5 empty] | 1 | 0 |  | 4 | 4 | [5 empty] | 8.5 | 8.5
F | 2025-03-14 | 102.2% | 85.14 | 87 | 6 | 2 | 22 | 22 |  |  |  | 23 | 7 | 2 | 2 |  | 1 | 1 |  |  |  | 16 | 36 | 2 | 0 |  | 8 | 6 |  |  |  | 1.14 | 0 |  |  |  | 10 | 10 | 1 |  |  |  |  | 1 | 0 |  | 4 | 5
Week Status |  | 110.5% | 618.03 | 682.89 | 12 | 12 | 132 | 132 | 1 | 1 |  | 235 | 251 | 4 | 4 |  | 10 | 10 | 0 | 0 |  | 137 | 201 | 4 | 3 |  | 64 | 47 | 0 | 1 |  | 6.03 | 5.89 | 0 | 2 |  | 16 | 16 | 1 | 1 |  | 0 | 1 | 2 | 0 |  | 18 | 19 | 0 | 0
M | 2025-03-17 | 104.2% | 151.47 | 157.89 | 1 | 4 | 11 | 8 |  |  |  | 100 | 107 |  |  |  | 3 | 3 |  |  |  | 20 | 20 | 1 | 1 |  | 12 | 12 |  | 1 |  | 1.47 | 0.89 | [5 empty] | Playback postponed on 14th Mar is completed today (17/Mar/25) | 1 | SECONDARY SUPPORT |  |  | Playback postponed on 14th Mar is completed today (17/Mar/25) | 1 | SECONDARY SUPPORT | 4 | 7 | [5 empty] | 4 | 4 | SECONDARY SUPPORT
T | 2025-03-18 | 83.55% | 155.47 | 129.89 | 2 | 2 | 11 | 14 | 2 |  |  | 112 | 91 |  |  |  | 3 | 3 |  |  |  | 12 | 2 |  | 1 |  | 13 | 13 |  |  |  | 0.47 | 0.89 | [11 empty] | 1 |  | 4 | 6
W | 2025-03-19 | 75.24% | 117.47 | 88.39 | 6 | 7 | 11 | 11 | 2 | 2 |  | 50 | 39 | 4 | 4 |  | 2 | 2 |  |  |  | 20 |  |  | 1 |  | 32 | 32 |  |  |  | 0.47 | 0.39 | [13 empty] | 2 | 4
T | 2025-03-20 | 85.02% | 85.14 | 72.39 | 14 | 15 | 11 | 11 | 12 | 12 |  | 28 | 27 | 1 | 1 |  | 2 | 5 |  |  |  | 16 |  | 1 | 1 |  | 23 | 23 |  | 1 |  | 1.14 | 0.39 | [13 empty] | 4 | 6
F | 2025-03-21 | 73.14% | 119.14 | 87.14 | 3 | 1 | 11 | 11 |  |  |  | 72 | 51 | 1 | 1 |  | 3 | 0 |  |  |  | 10 |  | 1 | 0 |  | 19 | 19 |  |  |  | 0.14 | 0.14 | [13 empty] | 4 | 6 | 1 | 1
Week Status |  | 85.21% | 628.69 | 535.7 | 26 | 29 | 55 | 55 | 16 | 14 |  | 362 | 315 | 6 | 6 |  | 13 | 13 | 0 | 0 |  | 78 | 22 | 3 | 4 |  | 99 | 99 | 0 | 2 |  | 3.69 | 2.7 | 0 | 0 | [11 empty] | 18 | 29 | 1 | 1
M | 2025-03-24 | 159.6% | 57 | 91 | 9 | 5 | 11 | 11 | 3 | 3 |  | 28 | 57 |  |  |  | 3 | 3 | [6 empty] | 2 |  | 10 | 14 | 6 |  |  | 1 | 2 | [13 empty] | 4 | 4
T | 2025-03-25 | 103.3% | 52.25 | 54 | 8 | 10 | 11 | 44 | 7 | 7 |  | 31 | 0 |  |  |  | 3 | 3 | [6 empty] | 1 |  | 3 |  | 1 |  |  | 0.25 | 0 |  | 2 | [11 empty] | 4 | 7
W | 2025-03-26 | 47.46% | 44.25 | 21 | 6 | 12 | 11 |  | 1 | 1 |  | 25 | 16 | 2 | 2 |  | 5 | 5 | 1 | 1 | [6 empty] | 1 |  | 1 | 2 |  | 0.25 | 0 | 1 | 6 | [11 empty] | 2 |  |  | 1
T | 2025-03-27 | 12.31% | 16.25 | 2 | 6 | 1 | 11 |  | 5 | 1 |  | 0 | 0 |  |  |  | 3 | 2 | [13 empty] | 0.25 | 0 | 1 | 0 | [11 empty] | 2
F | 2025-03-28 | 21.24% | 28.25 | 6 | 4 | 7 | 11 |  |  | 4 |  | 0 | 0 | 2 | 2 |  | 5 | 6 | 1 | 0 | [11 empty] | 1.25 | 0 | 1 | 1 | [11 empty] | 11
Week Status |  | 87.88% | 198 | 174 | 33 | 35 | 55 | 55 | 16 | 16 |  | 84 | 73 | 4 | 4 |  | 19 | 19 | 2 | 1 |  | 0 | 0 | 0 | 3 |  | 14 | 14 | 8 | 2 |  | 3 | 2 | 3 | 9 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 23 | 11 | 0 | 1 |  | 0 | 0 | 0 | 0
M | 2025-03-31 | 0% | 0 | 0 | 2 | 1 |  |  |  |  | SECONDARY SUPPORT |  |  |  |  | SECONDARY SUPPORT |  |  |  | 1 | SECONDARY SUPPORT |  |  |  |  | SECONDARY SUPPORT |  |  |  |  | SECONDARY SUPPORT |  |  | 2 | 0 | [15 empty] | SECONDARY SUPPORT
T | 2025-04-01 | 0% | 0 | 0 | 1 | 0 | [27 empty] | 1 | 0
W | 2025-04-02 | 0% | 0 | 0 | 1 | 0 | [27 empty] | 1 | 0
T | 2025-04-03 | 0% | 0 | 0 | 1 | 0 | [27 empty] | 1 | 0
F | 2025-04-04 | 0% | 0 | 0 | 1 | 0 | [27 empty] | 1 | 0
Week Status |  | 0% | 0 | 0 | 6 | 1 | [25 empty] | 0 | 0 | 6 | 0
M | 2025-04-07 | 0% | 0 | 0 | 0 | 0 | [29 empty] | SECONDARY |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY | [9 empty] | PRIMARY
T | 2025-04-08 | 0% | 0 | 0 | 0 | 0
W | 2025-04-09 | 0% | 0 | 0 | 0 | 0
T | 2025-04-10 | 0% | 0 | 0 | 0 | 0
F | 2025-04-11 | 0% | 0 | 0 | 0 | 0
Week Status |  | 0% | 0 | 0 | 0 | 0
M | 2025-04-14 | 0% | 0 | 0 | 0 | 0
T | 2025-04-15 | 0% | 0 | 0 | 0 | 0
W | 2025-04-16 | 0% | 0 | 0 | 0 | 0
T | 2025-04-17 | 0% | 0 | 0 | 0 | 0
F | 2025-04-18 | 0% | 0 | 0 | 0 | 0
Week Status |  | 0% | 0 | 0 | 0 | 0
M | 2025-04-21 | 0% | 0 | 0 | 0 | 0 |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY |  |  |  |  | PRIMARY | [14 empty] | PRIMARY
T | 2025-04-22 | 0% | 0 | 0 | 0 | 0
W | 2025-04-23 | 0% | 0 | 0 | 0 | 0
T | 2025-04-24 | 0% | 0 | 0 | 0 | 0
F | 2025-04-25 | 0% | 0 | 0 | 0 | 0
Week Status |  | 0% | 0 | 0 | 0 | 0
M | 2025-04-28 | 0% | 0 | 0 | 0 | 0 | [30 empty] | Handed Off |  |  |  |  | Handed Off | [9 empty] | Handed Off
T | 2025-04-29 | 0% | 0 | 0 | 0 | 0
W | 2025-04-30 | 0% | 0 | 0 | 0 | 0

## Risks
Sl. No. | Tower | Risk Item | Risk Reason / Description | Mitigation | Impact if not mitigated | Originator | Reported Date | Due Date | Risk Owner | Impact if not mitigated by due date | Status | Closed Date